## Sheet1
Risk No. | Risk | Description | Potential Effect | Risk Owner | Risk Assessment |  |  | Treatment
[5 empty] | Probability | Impact | Risk Level
COTS (Commercial Off the Shelf) solution
1 | Inadequate support of COTS vendor | The COTS vendor may stop providing support or provide inadequate support either due to incompetency or bankruptcy | Inadequate service quality
Security breaches and incidents
Non-compliance with regulatory authority
Financial loss and reputational damage
2 | Process risk | The COTS application may require more time than required to understand and integrate business processes | Sustainability of application leading to service degradation
3 | SLAs not meeting agreed-on metrics | Depending on the support model agreed, the vendor could breach the SLA | Not able to provide the agreed-on RTO and RPO
4 | Product obsolescence | Lack of product enhancements and/or product development may get dropped | Inadequate service quality
Security breaches and incidents
Financial loss and reputational damage
Not able to meet organisations strategic objectives
Open-Source solution supported by Internal IT department
1 | Software quality | Open source projects are community-oriented, developed and supported through collaboration. However with insufficient resources, quality will suffer. | Inadequate service quality
Not able to meet strategic objectives
2 | Sustainability over longer time period | As open-source projects relies on community contributions, if the contributors are not able to keep the commitment, it will lead to a product that is no longer sustainable | Inadequate service quality
Security breaches and incidents
Not able to meet organisations strategic objectives
3 | Copyright infringement | Negligence from coder can potentially allow proprietary code in the product. | Financial loss and reputational damage
4 | Software security risks | Open-source vulnerabilities and exploits are made public to everyone once discovered. If there is a vulnerable open-source library used in the code, there is a risk of malicious attack. | Security breaches and incidents
Financial loss and reputational damage
In-house developed solution built by a student and supported by Internal IT department
1 | Unrealistic estimated schedule | The solution developed by the student may have unrealistic deadline for completion | Not able to meet organisations strategic objectives
2 | Lack of adequate skill set | The solution may suffer quality issues and/or not meet the expectations due to a lack of required skill set | Not able to meet organisations strategic objectives
Security breaches and incidents
Inadequate service quality
3 | Incomplete solution | There is a risk of an incomplete solution if the student discontinues the course | Not able to meet organisations strategic objectives
4 | Lack of upper management involvement | Risk of upper management not being involved with the student | Not able to meet organisations strategic objectives
5 | Insufficient testing | There is a risk of the solution not being tested sufficiently either due to project timelines or inadequate skillset | Security breaches and incidents
Inadequate service quality
References:
Software Engineering Authority. (2017). Understanding the Risks of Commercial off-the-shelf software (COTS). [online] Available at: https://ao.ms/understanding-the-risks-of-commercial-off-the-shelf-software-cots/ [Accessed 22 Mar. 2022].
‌snyk.io. (2021). 5 Risks of Open Source Software ¦ Snyk. [online] Available at: https://snyk.io/learn/risks-of-open-source-software/ [Accessed 22 Mar. 2022].
WhiteSource. (n.d.). Top 3 Open Source Risks and How to Beat Them. [online] Available at: https://www.whitesourcesoftware.com/resources/blog/top-3-open-source-risks-and-how-to-beat-them/ [Accessed 23 Mar. 2022].
ResearchGate. (n.d.). Table 5 . Top ten risks factors in inhouse & outsourced software projects. [online] Available at: https://www.researchgate.net/figure/Top-ten-risks-factors-in-inhouse-outsourced-software-projects_tbl2_319643465 [Accessed 24 Mar. 2022].
‌Information Systems Audit And Control Association (2013). CRISC review manual 2014. Rolling Meadows, Ill.: Isaca.